## Slide 1
Engineering Commissioning
SKA1 LOW – Assembly, Integration & Verification
Adam MacLeod
AIV Consortium Manager & ASKAP System Engineer

## Slide 2: Introduction
The AIV Consortium
The SKA1 Low Roll Out Plan
Handover & Sell-Off, Support & Maintenance

## Slide 3: The AIV Consortium
Responsible for planning Assembly, Integration and Verification of the two SKA1 telescopes in construction.
Consortium partners:
  SKA SA (lead organisation)
  Focus on SKA1 MID
  CSIRO & ASTRON
  Focus on SKA1 LOW
Notes: Assembly – Creation of baselined platforms.
Integration – Testing and demonstration of functionality.
Verification – against L1 requirements
Not just the orange box, but the managerial/contractual interfaces to the adjacent boxes as configuration items change hands.
AIV is a process that will have clearly defined inputs and outputs.

## Slide 4: SKA LOW Roll Out Plan
Based on an iterative process of Assemble, Integrate and Verify. Allow the array to grow and evolve over time.
Notes: Early validation of element interfaces.
Early demonstration of system functionality.
Early assessment of system performance.
Early mitigation of technical risks.

## Slide 5: SKA LOW Roll Out Plan
Array Assemblies vs. Array Releases
  Array Assembly refers to the assembled platform at the start of integration. i.e. input to the AIV process.
  Array Release refers to the platform at the end of planned verification activities. i.e. output from the AIV process.
Array Assemblies are defined by their size (number of stations), functionality and expected dates in construction.
  Implies dependencies from element level consortia.
  A small amount of flexibility has been built in to address early/late delivery of components.
AIV Planning is based on a 5 year construction schedule.
Notes:   Configuration baseline for each platform => The sum of its parts.
  Note: Timeline has been removed from Revision 4 of the Roll Out Plan as requested by the SKA Office. However it is implied by the AIV Cost Model. It is also central to all AIV planning.

## Slide 6: SKA LOW Roll Out Plan AA1
AA-1 | Description
Date | TBD
Number of Stations | Up to 12
Array Capability | Baselines: At least one station on a long baseline. Baseline should be long enough to demonstrate the fringe rotation functionality. AA-1 Stations are to be located away from the centre of Low Central Core either along a spiral arm or on the outer skirt of the Central Core in a suitable configuration for basic imaging. Frequency Band: SKA1 LOW Correlator Bandwidth: 100MHz Correlator Size: up to 12 station correlator Channelisation: Standard fine channelization (64k channels) Imaging Functionality: Beamforming and Continuum Imaging Spectral Line Imaging Non-Imaging Functionality: Raw data capture at the beamformer input and output Test waveform generator Distortion detection No Zoom mode Pulsar Search 1 beam (PSS) Pulsar Timing 1 beam (PST) Operational Functionality: Full Operator & Maintainer Interface, including POST, BIT and alarm handling. Support for scheduled observation blocks (max SNR Beamformer weights calculated offline) Scalable hardware correlator Offline imaging
Notes:   AA1 – scaling from one -> 4 -> 12 stations
  3 superstation locations on the southern side of the core.
  Backend located in an RPF.

## Slide 7: System Level ITF
AIV has generated a business case and draft requirements for a system level ITF
  Describe a staging platform for off-site system level integration.
  These are based on the system level ITF we use for ASKAP.
  Focused on back-end assemblies.
This facility will support first-stage integration of complex SKA1-Low sub-systems. It should allow interfaces and interoperability of the sub-systems to be demonstrated and tested. It should provide a convenient environment for collaboration between teams working in different technical domains. It should allow ease of fault isolation and issue resolution. Most first-stage integration work is either impractical or infeasible to do at site.
Notes: Running parallel to the on-site integration and verification activities….
Tests facilitated and overseen by AIV

## Slide 8: Notes on the ITF
Risk reduction in roll out of HW, SW, FW.
Implies that the platform evolves, but does not necessarily grow, over time.
Similar ITF being planned for SKA1 Mid in South Africa
  Currently being designed in to the new SKA SA headquarters.
Not currently funded or in scope of the project. However the existence of a system level ITF for Low is a working assumption.
  Location not specified. Accessibility and availability is.
  Its usage is described in the Roll-Out Plan, the AIV Cost model, and the I&V Plans.

## Slide 9: Notes on the ITF
ITF Construction:
  AIV has not costed and will not design or build the ITF.
  AIV will continue to provide input on ITF business case and requirements.
ITF Operation:
  AIV has a component of labour in its cost model which could be directed towards operating an ITF. This would only partially cover the operating costs.
ITF Integration and Test Activities:
  AIV has included labour for managing and conducting testing within the ITF.
  AIV will coordinate, witness and participate in integration tests which are undertaken.
  Testing will be mostly informal, sometimes formal. The ITF will be used continually throughout construction.
  Training, Integration Readiness Reviews, handover and sell-off will be facilitated. Processes are TBD but contractors likely to sell-off against L2 requirements, and provide support/maintenance on top of that.
  Planned use of ITF by consortia: variable. ITF usage not mandated.

## Slide 10: Product Handover & Selloff
AIV will accept products which are proven to be Integration Ready
The criteria is documented in the AIV Handover Checklist. E.g. assessment based on …
Configuration Items.
Proof of completeness
Proof of correctness
Outstanding issues, ECPs & waivers
Asset tracking
Product support and maintenance
This becomes inseparable from contractor sell-off and contractor milestones.
  Discussions with the SKAO are starting. What kinds of contractual clauses?
  The AIV contractor will probably need to be an agent of SKAO
Notes: Process will be tailored for:

## Slide 11: Product Handover & Selloff
Handover process will need to be tailored for:
Different types of Configuration Items.
Qualification testing versus Acceptance testing.
Patches and regression testing
Required level of Validation of L2 interfaces.
  Support and Maintenance
  The ITF allows Validation of L2 interfaces (element to element).
  AIV requires product support and maintenance through the construction phase
    Design Support
    Provision and replacement of products
    Again….Discussions with the SKAO are starting. What kinds of contractual clauses?
Notes: Process will be tailored for:

## Slide 12: Next steps for AIV
Refinement of the Roll Out Plans for SKA1 Low
  Include dates to help create construction schedule dependencies.
  Increased level of detail on Array Assembly functionality.
  Respond to changes in L1 requirements.
  Elaborate on the use of Sub Arrays.
Refinement of the Hand Over Checklist
  Tailored handover processes based on CI type.
  Open discussion on contractual clauses to support Handover, Product Support and Product Maintenance
Creation of detailed test procedures for SKA1 Low
  Integration tests and verification tests for each Array Assembly
  Well underway.
Notes: Process will be tailored for: